## Backlog - courant
Product Backlog
Update : 09/03/2021
ID | Category | Requested by | Task | Definition of Done | Priority | Who? | Workload | Not validated | Demo OK on: | Notes | Reference document
7 | Development | P.O | Create Class "Game" | Class created and operationnal | 85 | S. Zid | 0h30 |  | 2021-03-17
9 | Development | S. Zid | Create Class "Game Panel" | Class created and operationnal | 80 | C. Zimmerlin | 0h30 |  | 2021-03-17
11 | Development | P.O | Create Class "Menu State" | Class created and operationnal | 70 | T. Vitry | 0h45 |  | 2021-03-17
10 | Development | S. Zid | Create Class "Game State" | Class created and operationnal | 70 | S.Zid | 0h45 |  | 2021-03-17
12 | Development | P.O | Create Class "Level State" | Class created and operationnal | 70 | P. Notte | 0h45 |  | 2021-03-17
8 | Development | P. Notte | Create Class "Map Object" | Class created and operationnal | 65 | S. Zid | 1h |  | 2021-04-01
15 | Development | P.O | Create Class "Cell" | Class created and operationnal | 55 | C. Zimmerlin | 1h |  | 2021-04-01
13 | Development | P.O | Create Class "Wall" | Class created and operationnal | 55 | T. Vitry | 1h |  | 2021-04-01
16 | Development | P.O | Create Class "Player" | Class created and operationnal | 60 | B. Roche | 2h |  | 2021-04-01
14 | Development | P.O | Create Class "Bomb" | Class created and operationnal | 55 | P. Notte | 1h |  | 2021-04-01
4 | Development | ScrumMaster | Create a "Main" Package | Package created | 30 | B. Roche | 0h02 |  | 2021-03-09
5 | Development | ScrumMaster | Create a "State" Package | Package created | 30 | B. Roche | 0h02 |  | 2021-03-09
6 | Development | ScrumMaster | Create an "Entity" Package | Package created | 30 | B. Roche | 0h02 |  | 2021-03-09
17 | Development | P.O | Create Bonus | Bonus elaborated and implemented | 0 | TBD | 1h30 |  | 2021-05-10
18 | Development | P.O | Multiplayer | Multiplayer elaborated and implemented | 0 | TBD | 2h |  | 2021-05-10
1 | Project definition | Client | Define the project | When the goals of the project have been clearly defined | -1 | Client and P.O | 1h |  | 2021-02-18
2 | UML Diagram | Client | Elaborate and draw the UML Diagram for the 10/03 | The UML has been presented the 10th of March | -1 | P.O | 1h30 |  | 2021-03-09
3 | Coordination | ScrumMaster | Creation of the Github | GitHub created | -1 | ScumMaster | 0h30 |  | 2021-02-24
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86

## Légende
Fini-Fini
Fini
==> | Décalé à la période suivante
Abandonné

## Burndownchart - sprint 1
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
| 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-29 | 2013-07-30 | 2013-07-31 | 2013-08-01 | 2013-09-02 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06